## ERCIP
Program Year |  |  |  |  | Last Updated: | 2022-12-27 |  |  |  | P&D Funds | [5 empty] | Construction Funds | [9 empty] | Estimated Dates |  | A/E 1 for 0-35% design |  |  |  | A/E 2 for 35% design to construction
Fiscal Year of Appropriation | Installation | Project # | Project Title | Status | Next Steps | MCICOM GF-PW Action | Notes / Additional Information | Project Description | Mission Alignment | Initial Submission Amount (Planning 1391) ($000) | President's Budget Amount (Budget Ready 1391) ($000) | Original Authorized Amount ($000) | Current Authorized Amount ($000) | Current Working Estimate ($000) | Amount Awarded ($000) | Initial Submission Amount (Planning 1391) ($000) | President's Budget Amount (Budget Ready 1391) ($000) | Original Authorized Amount ($000) | Current Authorized Amount ($000) | Current Working Estimate ($000) | Appropriation Allocated ($000) | Amount Awarded ($000) | Construction Agent | Acquisition Strategy | Congressional Authorization | Final Design Authority (FDA) | Design Direction (from Project Sponsor) | RFP for D/B RFP Complete (D/B RFP Award) | D/B RFP Start | 35% Design | D/B RFP Complete | Contract Award (D/B Award) | Construction Start Date | Construction Completion Date (CCD) | Beneficial Occupancy Date (BOD) | Full Operational Capability (FOC)
2009 | MCB Camp Lejeune | P-1282 | Solar Heating, Training Pools | Complete | - | - | - | - | - | [8 empty] | 1082 |  |  | 869.755 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2009 | MCB Camp Lejeune | P-1142 | Steam Decentralization Courthouse Bay | Complete | - | - | - | - | - | [13 empty] | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2009 | MCB Hawaii | HI0936R | Solar Hot Water Systems for Temporary Lodging Facility, Bldgs 3038, 6533-6536 & 6539 | Complete | - | - | - | - | - | [8 empty] | 29 |  |  | 503.544 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2009 | MCAGCC 29 Palms | P-181 | Photovoltaic System, Buildings 2056, 2057 & 2058 (Vehicle Holding Sheds) | Complete | - | - | - | - | - | [8 empty] | 1159 |  |  | 1159 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2009 | MCAS Camp Pendleton | PA0904R | Photovoltaic System & Exterior Lighting Ph II, B23208 (Aviation Armament Shed) | Complete | - | - | - | - | - | [8 empty] | 1135 |  |  | 1202.022 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | - | 0
2009 | MCAS Miramar | P-982 | Landfill Distribution Line | Complete | - | - | - | - | - | [8 empty] | TBD |  |  | 915 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2009 | MCAS Miramar | MI0981R | Solar Wall, Solar Thermal DHW, Solar Electric - Building 9215 | Complete | - | - | - | - | - | [8 empty] | 877 |  |  |  |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2010 | MCRD Parris Island | P-392 | PV System - Parade Deck | Complete | - | - | - | - | - | [8 empty] | 1516 |  |  |  |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2010 | MCAGCC 29 Palms | P-200 | PV System | Complete | - | - | - | - | - | [8 empty] | 1618 |  |  | 1573.228 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2010 | MCAS Miramar | P-305 | PV System | Complete | - | - | - | - | - | [8 empty] | 1790 |  |  | 1737.968 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2010 | MCAS Miramar | P-214 | PV System | Complete | - | - | - | - | - | [8 empty] | 2872 |  |  | 3437.674 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2011 | MCAS Cherry Point | P-935 | Facility Energy Improvements | Complete | - | - | - | - | - | [8 empty] | 1656 |  |  | 1584.307 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2011 | MCLB Albany | P-960 | Ground Source Heat Pumps | Complete | - | - | - | - | - | [8 empty] | 4748 |  |  | 5327.449 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2011 | MCB Camp Pendleton | PE1291M | Solar Thermal & PV - Area 43 Training Pool | Complete | - | - | - | - | - | [8 empty] | 729 |  |  |  |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2012 | MCB Camp Lejeune | P-1422 | Steam Decentralization Camp Geiger | Complete | - | - | - | - | - | [8 empty] | 6925 |  |  | 6474.468 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2012 | MCLB Albany | P-961 | Landfill Gas Generator | Complete | - | - | - | - | - | [8 empty] | 3504 |  |  | 4705.502 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2013 | MCB Camp Lejeune | P-1449 | Steam Decentralization Courthouse Bay | Complete | - | - | - | - | - | [8 empty] | 5701 |  |  | 5622.179 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2013 | MCB Quantico | P-687 | Micro Turbine Plant | Complete | - | - | - | - | - | [8 empty] | 7943 |  |  | 7942.894 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2014 | MCAS Miramar | P-906 | Base Wide Micro Grid with Renewable Pwr | Complete | - | - | - | - | - | [8 empty] | 17968 |  |  | 22057.697 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2015 | MCB Hawaii | P-932 | District CHW and HW Plant | Complete | - | - | - | - | - | [8 empty] | 4166 |  |  | 4286.378 |  | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2015 | MCB Hawaii | P-917 | Utility Monitoring and Controls | Cancelled | - | - | - | - | - | [8 empty] | 4294 | N/A |  | N/A | N/A | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2016 | MCAS Beaufort | P-1254 | Construct Multiple Project Shelters with PV at Facility 1254, MVP | Cancelled | - | - | - | - | - | [8 empty] | 5740 | N/A |  | N/A | N/A | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2016 | MCB Camp Pendleton | P-1692 | Microgrid Expansion | Cancelled | - | - | - | - | - | [8 empty] | 1695 | N/A |  | N/A | N/A | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2017 | MCAS Beaufort | P-1337 | Chilled Water Storage | Cancelled | - | - | - | - | - | [8 empty] | 1395 | N/A |  | N/A | N/A | NAVFAC | - | - | - | - | - | - | - | - | - | - | - | - | -
2018 | MCB Camp Lejeune | P-1487 | Camp Johnson Microgrid | Construction | Finish construction | None | Cost increase for construction award covered using cancelled funds from P-938 and P-975 (OSD approved May 2022). | Provide microgrid with upgraded electrical infrastructure, 5 MW of on-site natural gas-fired generation, a 5.4-MW BESS, integration of an existing solar PV system for demand management, black start and islanding. | This project supports mission assurance and readiness by…. This project addresses known vulnerabilities associated with XXXX | [8 empty] | 9750 | 23264 | 23264 | 23264 | 23264 | NAVFAC | UESC + ERCIP |  | 2019-02-06 | 2019-02-01 | 2020-11-19 | 2020-11-19 | 2021-04-02 | 2022-07-21 | 2022-09-29 | 2023-06-01 | 2025-12-15 | 2025-12-15 | 2025-12-15
2018 | MCB Hawaii | P-938 | District CHW and DHW Plant for Bldgs. 7046, 7047, 4057-7059 | Cancelled | - | - | Cancelled due to bid bust. Funds reprogrammed to support cost increase for P-1487 (OSD approved May 2022). | [10 empty] | 6185 | N/A | 11760 | N/A | N/A | NAVFAC | TBD | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2018 | MCAS Miramar | P-260 | Reclaimed Water Expansion Project | Complete |  |  | - | [10 empty] | 1398 |  |  |  |  | NAVFAC | TBD | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2019 | MCAS Beaufort | P-505 | Electrical Hardening and Black Start CHP System | RFP/Design | J&A, Legal Sufficiency Review, and Finish IGA | Continue to engage in J&A and legal sufficiency review discussions. | In design via UESC IGA | Minimize risk of Station-wide power outage by burying overhead electrical lines and build microgrid backbone. | This project supports mission assurance and readiness by…. This project addresses known vulnerabilities associated with XXXX | [8 empty] | 22765 |  |  |  |  | NAVFAC | UESC + ERCIP |  |  |  | 2020-02-14 | 2020-02-14 | 2020-11-11 | 2023-04-28 | 2023-06-30 | 2024-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01
2019 | MCLB Albany | P-975 | Replace Hardness Treatment in Water | Cancelled | - | - | Cancelled due to bid bust. Funds reprogrammed to cover cost overruns for other projects (OSD approved May 2022). | Modernize the water treatment plant and improve potable water quality | [9 empty] | 10015 | N/A |  | N/A | N/A | NAVFAC | TBD | n/a | 2021-02-01 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2019 | MWTC Bridgeport | P-480 | MWTC Bridgeport Energy Resilience Phase 1 & 2 | Awarded | Award P-481, Phase 2 low voltage work. | None | Cost increase covered using cancelled funds from P-975 (OSD approved May 2022). | Modernize electrical system to enhance system reliability and prepare to build basewide microgrid. | This project supports mission assurance and readiness by modernizing the electrical distribution system basewide. This project addresses known vulnerabilities associated with [get from IESP] | [8 empty] | 4729 |  |  |  |  | NAVFAC | Design/Build | n/a | 2020-02-01 | 2020-03-01 | 2020-06-09 | 2020-06-09 | 2020-08-06 | 2023-04-04 | 2023-04-19 | 2024-01-19 | 2026-01-17 | 2026-01-17 | 2026-01-17
2020 | MCAS Camp Pendleton | P-143 | Advanced Microgrid Infrastructure Improvement | Acquisition | Determine how to move forward. | Engage with MCAS CP / MCIWEST to determine path forward given bid bust. |  | Build Station micro-grid by integrating existing generators, a new battery, and new controls to centrally power critical facilities during an outage (target 14 days) | This project supports mission assurance and readiness by…. This project addresses known vulnerabilities associated with XXXX | [8 empty] | 7321 |  | 13 |  |  | NAVFAC | Design/Build | n/a | 2019-09-01 |  | 2020-02-14 | 2020-02-14 | 2021-04-09 | 2021-11-30 | 2023-02-01 | 2023-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01
2020 | MCAS Miramar | P-266 | Additional Water Supply for Resilience | Construction | Finish construction | None | Cost increase covered using cancelled funds from P-975 (OSD approved May 2022). | Mitigate water quality issues in East Miramar and provide water resilience by adding a new redundant water supply connection to supplement existing system. | This project supports mission assurance and readiness by…. This project addresses known vulnerabilities associated with XXXX | [8 empty] | 4315 |  |  |  |  | NAVFAC | Design/Build | n/a | 2019-02-01 |  | 2019-11-22 | 2019-11-22 | 2020-01-15 | 2020-05-15 | 2020-11-03 | 2020-12-01 | 2023-03-10 | 2023-03-10 | 2023-03-10
2021 | MCAGCC 29 Palms | P-1238 | 10 MW Battery Energy Storage | RFP/Design | Finish RFP |  | CWE is has doubled to tripled due to inflation, supply chain, battery technology, communications, and new UFC. UFC 3-600-01 requires 100’ lithium (Li) BESS occupied area standoff distance (where solar PV is located) so new site plan was required. | 10.6 MW BESSs to support 54 solar PV systems for clean energy charging. Provide cybersecurity. | This project supports mission assurance and readiness by…. This project addresses known vulnerabilities associated with XXXXReduce critical training mission downtime by improving electrical reliability due to solar PV production variations. Improve mission readiness by building capability to black start and island critical missions with on site generation, BESSs, and microgrid operations. | [8 empty] | 11646 |  |  |  |  | NAVFAC | Design/Build | n/a | 2020-02-12 |  | 2021-07-08 | 2021-07-08 | 2022-05-01 | 2023-05-30 | 2024-01-31 | 2024-11-01 | 2026-11-01 | 2026-11-01 | 2026-11-01
2022 | MCAS Miramar | P-281 | Additional LFG Power Meter Station | RFP/Design | Finish RFP | NLT 1/3, provide OSD updated CTC | None | Build en electrical feeder that allows use of additional landfill gas. | Support mission critical functions associated with the 3rd Marine Air Wing and the national/state Emergency Operations Center by providing capabiltiy to use additional landfill gas power. | [8 empty] | 4054.189 |  |  |  |  | NAVFAC | Design/Build |  | 2022-04-19 |  | 2022-06-02 | 2022-06-02 | 2022-11-01 | 2023-06-30 | 2023-08-03 | 2024-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01
2023 | MCMWTC Bridgeport | P-481 | Microgrid and Backup Power, Phases 3 and 4 | RFP/Design | Finish RFP | NLT 1/3, provide OSD updated CTC | None | Build microgrid that provides 3 MW+ of backup power generation and an estimated 3 MW BESS to support normal and contingency operations due to extreme weather (snow, fire), infrastructure failure, or other unanticipated events. | This project supports mission assurance and readiness by…. This project addresses known vulnerabilities associated with XXXX | [8 empty] | 25560 |  |  |  |  | NAVFAC | Design/Build |  | 2021-09-30 |  | 2021-12-09 | 2021-12-09 | 2023-02-01 | 2023-06-14 | 2024-01-17 | 2024-10-17 | 2026-10-17 | 2026-10-17 | 2026-10-17
2024 | MCAS Miramar | P-283 | Electrical Infrastructure, On-Site Generation, and Microgrid Improvements | Planning |  |  |  | Bolster reliability and resilience of microgrid by replacing underground electrical distribution infrastructure (cabling and T-bodies) and installing 1 MW solar PV, a 1.9 MW BESS, and 1.4 MW of standby generators. | Project addresses gaps in the Station’s energy security posture identified during Energy Resilience Readiness Exercises and in the IESP relating to lack of onsite generation, aged electrical systems, and insufficient monitoring/control capabilities. Provide improved electrical reliability and resilience to the microgrid which serves critical aviation missions. | [8 empty] | 30550 |  |  |  |  | NAVFAC | TBD, Ideally UESC |  | 2022-12-01 |  | 2023-02-01 | 2023-02-01 | 2023-06-01 | 2024-02-01 | 2024-07-01 | 2024-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01
2025 | MCAS Beaufort | P-507 | Microgrid and Backup Power | RFP/Design | DE/Noresco finish IGA. Determine if project is funded for FY25 ERCIP before determining if project will get folded into UESC. | None |  | This project will construct a 2.8 MW gas-fired CHP plant, a 500-kW solar PV system, a 1.25-MW/2.5-MWh BESS, and a Station-wide microgrid. Work includes interconnection agreements, cybersecurity, and commissioning. The project is required to close IESP gaps associated with inadequate backup power and fuel for critical aviation missions, provide 100% resilience to the mobile aviation maintenance van pad facility, and comply with energy resilience policy (DODI-4170.11 and MCICOM Energy Security Policy Letter 9-19) and cyber requirements. | This project enhances mission assurance and aviation readiness by providing the capability to operate 14+ days without commercial power (with the support of FY19 ERCIP P-505) and by providing uninterruptable power to the critical MALS-31 mobile van pad maintenance mission. This project addresses known vulnerabilities associated with reliance on the commercial power grid, climate impacts (e.g., hurricanes, tornadoes, lightning strikes), and manmade threats (e.g., conflicts, terrorist attacks, cyberattacks) by installing onsite generation, storage, and controls that reduce the Station’s reliance on utilities from outside the fence. | [8 empty] | N/A | N/A | 36623 | N/A | N/A | N/A | UESC + ERCIP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | CATC Fuji | P-904 | Microgrid and Backup Power | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | Determine if Gov wants to start navigating ESPC + ERCIP |  | This project will bring natural gas to Camp Fuji and install one 400-kW gas-fired reciprocating CHP generator, one 400-kW gas-fired peaking generator, one 400-kW diesel-fired standby generator, and one 367 kW-DC solar PV system, carport-mounted. Additional electrical work will include modernizing the electrical distribution system by replacing aged transformers, upgrading/replacing the main substation, and replacing electrical feeders camp-wide. Additional mechanical work will include decentralizing the Lower Camp boiler plant, installing gas-fired satellite boilers at select facilities, and modernizing the Upper Camp boiler plant to be dual fuel-fired. A microgrid controller will be installed and generation assets will be connected to the microgrid and the system will be cybersecured. The project is required to close IESP gaps associated with inadequate generation and refueling plans. The project also enhances energy and climate security per Federal policy requirements and better positions MCIPAC to achieve General Berger’s (38th Commandant) objective to have stand-in fight capability at MCIPAC installations. | This project supports mission assurance and readiness at Camp Fuji by providing the Camp with a reliable, resilient, and cybersecure microgrid that enables islanding and continuity of operations for 14+ days for the entire Camp. This project supports mission critical functions by allowing all functions, including mission critical training, to continue operations without disruption. This project addresses known vulnerabilities associated with potential climate impacts (e.g., typhoons), and manmade threats (conflict, terrorist attack, cyberattack, etc.), aging infrastructure, inadequate backup power, and insufficient staffing. Vulnerabilities are mitigated by replacing aged electrical and mechanical systems with modern, efficient, and reliable systems. In addition, the onsite generation and microgrid control system mitigate vulnerabilities associated with relying on the commercial power grid and limited backup generators for backup power. | [8 empty] | N/A | N/A | 41470 | N/A | N/A | N/A | ESPC + ERCIP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCB Camp Butler | P-312 | Microgrid and Backup Power, Camp Foster | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | Determine if Gov wants to start navigating ESPC + ERCIP |  | The project will construct a microgrid with a 5 MW natural gas fired CHP, a 1 MW solar PV system, a 1 MWh BESS, a new gas line, and 4.5 MW of standby-only diesel generation. The project also will provide critical electrical infrastructure upgrades and cybersecurity. The project is required to remove unacceptable energy risks and close IESP gaps associated with inadequate backup generation and fuel. The project also enhances energy and climate security per Federal policy requirements and better positions MCIPAC to achieve General Berger’s (38th Commandant) objective to have stand-in fight capability at MCIPAC installations.. | This project supports mission assurance and readiness at Camp Foster by providing a microgrid to power Feeders 1 and 2 at Camp Foster which provide power to multiple critical facilities that support mission essential functions, critical installation services, and continuity of operation plans. This project addresses known vulnerabilities identified in the IESP regarding inadequate backup power and insufficient backup fuel as well as will help mitigate climate change hazards (e.g., typhoons, rainfall, extreme heat, flooding) by installing onsite generation (including conventional generation and renewable energy), storage, and a microgrid to support warfighter missions during normal and contingency operations. | [8 empty] | N/A | N/A | 58570 | N/A | N/A | N/A | ESPC + ERCIP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCLB Albany | P-988 | Microgrid and Advanced Metering Improvements | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | None |  | This project will provide microgrid and AMI improvements. The microgrid work includes upgrading the electrical system (e.g., reclosures, pad and pole-mounted switches, etc.) from a mostly manual 12.47 kV power distribution system that uses conventional overcurrent protection and circuit controls to a modern power distribution system with a fully integrated protection, automation, and SCADA system with a real time display. Other improvements include new generator controls, communication infrastructure, and microgrid control system programming, simulations, and testing. AMI improvements include substation-level electrical metering as well as building-level water and gas meters. The project is required to close IESP gaps associated with aged electrical components, an inadequate AMI system, and the need for more cybersecure control systems to ensure energy availability for critical missions and to comply with Federal energy requirements. | This project enhances mission assurance and supports mission critical functions by improving microgrid automation to increase power availability and reduce disruption risks associated with manual electric system operations, lack of meter data, and inadequate cybersecurity. This project addresses known vulnerabilities by providing microgrid, metering, SCADA, and cybersecurity improvements that provide a smarter, automated microgrid that uses real-time data to island the base and power mission critical loads during contingency events, such as hurricanes. | [8 empty] | N/A | N/A | 13320 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCAGCC Twentynine Palms | P-1260 | Water Resilience for Critical Water Systems, Phase 1 | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | None |  | This project will replace the Upper, Middle and Lower Well Field Piping Network (~11.4 miles) that provides water from 11 of 13 wells to equalizer tanks and the 15th Street Piping Network on Mainside (~1.2 miles) and will install a new 30,000-gal Rifle Range water tank with controls and backup power. This water resilience project is the first of a two-phase requirement to address IESP gaps associated with an unreliable and inefficient potable water system. The project is required to increase MCAGCC’s confidence in providing potable water to critical missions during normal and contingency operations. | This project enhances mission assurance and supports mission critical functions by closing water resilience IESP gaps and improving base’s confidence in providing potable water to critical missions by replacing the aged Upper, Middle, and Lower Well Field Piping Network and the 15th Street Water Main System and installing a new water tank to provide fire protection requirements at the Rifle Range. The project also addresses known vulnerabilities associated with water leaks that contribute to climate-related hazards such as drought. | [8 empty] | N/A | N/A | 32760 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCAGCC Twentynine Palms | P-1261 | Water Resilience for Critical Water Systems, Phase 2 | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | None |  | This project will replace the “B-Line” water main (~8.4 miles) that conveys water from the well fields to the Mainside 15th St tie and the overhead 34.5 kVA electrical distribution system (~8.0 miles) that provides well field power. This water resilience project is the second of a two-phase requirement to address IESP gaps associated with an unreliable and inefficient potable water system. The project is required to increase MCAGCC’s confidence in providing potable water to critical missions during normal and contingency operations. | This project enhances mission assurance and supports mission critical functions by closing water resilience IESP gaps and improving base’s confidence in providing potable water to critical missions by replacing the aged B-Line water system and installing a new well field electrical distribution system. The project also addresses known vulnerabilities associated with water leaks that contribute to climate-related hazards such as drought. | [8 empty] | N/A | N/A | 35600 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCSF Blount Island | P-035 | Renewable Energy and Electrical Upgrades | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | None |  | This project will install a 1 MW solar PV system and 1 MWh BESS, provide dual fuel conversion for five generators, install ten Level 2 chargers/EVSE systems, modernize the building management and metering system modernization, retrofit lighting systems, and provide cybersecurity. This project is required to remove unacceptable energy risks identified in the draft IESP associated with energy availability requirements for critical missions. The project also is required to enhance energy security and cybersecurity and reduce greenhouse gases per Federal policy requirements. | This project supports mission assurance and mission critical functions by providing more reliable, resilient, and efficient power to critical facilities to support the mission to provide warfighters with the best combat-ready equipment and supplies to enable the rapid arrival and assembly of Marine Air Ground Task Forces. This is accomplished by installing solar PV systems and BESSs and converting existing generators to dual fuel to ensure fuel availability. This project addresses known energy security (i.e., energy reliability, resilience, and efficiency), climate (climate mitigation via greenhouse gas emissions reduction and climate adaptation by installing assets with flooding as a consideration), and cybersecurity vulnerabilities by installing and cybersecuring onsite power generation and storage assets, modernizing and cybersecuring building control systems, and completing lighting retrofits. | [8 empty] | N/A | N/A | 23860 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | Marine Barracks Washington | P-223 | Electrical Modernization and EVSE | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | None |  | This project will install one 300-kW natural gas fired generator to serve two critical facilities and three manual transfer switches and quick connects for three trailer mounted generators to serve four facilities. The project also will replace aged switchgears serving multiple critical facilities and build four Level 2 electric vehicle charging stations. The project is required to remedy reliability and resiliency gaps identified in the IESP per MCICOM Energy Security Policy Letter 9-19 and comply with EO 14057 and EO 14008 for fleet electrification. | This project enhances mission assurance and supports mission critical functions that provide critical Presidential, Commandant, and other senior leadership support missions by improving electrical system reliability and resiliency at critical facilities by replacing end of life electrical components, installing a stationary backup generator, and providing infrastructure for three mobile backup generators. The project addresses known vulnerabilities by closing seven IESP gaps and addressing climate hazards (e.g., increasing energy demand) by providing provisions to power critical missions with reliable and resilient onsite electrical systems. | [8 empty] | N/A | N/A | 2270 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCAS Iwakuni | P-1016 | Microgrid and Backup Power, Phase 1 | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | Determine if Gov wants to start navigating ESPC + ERCIP |  | This project is the first phase of a two-phase ERCIP effort to enhance energy security for the MCAS Iwakuni flight line. Proposed construction in Phase 1 includes the following: an estimated 5,000 SF generator building, two 2,500-kW gas-fired engines, one 2,500 kW diesel-fired standby generator, an estimated 35,000-gallon diesel storage tank, diesel fuel distribution piping/equipment, associated mechanical and electrical work, utility interconnections, microgrid and other controls, commissioning, and cybersecurity. Supporting work includes site preparations, gas distribution piping to generator building and central utility plant, a Station-wide communications/fiber network for the microgrid, and associated shipping/offloading costs for the equipment in Japan. The project is required to remove unacceptable energy risks and close IESP flight line vulnerabilities associated with inadequate generation and fuel delivery. The project also enhances energy security per Federal policy requirements and better positions MCIPAC to achieve General Berger’s (38th Commandant) objective to have stand-in fight capability at MCIPAC installations. | This project will enhance mission assurance and readiness by providing MCAS Iwakuni with 7.5 MW of onsite generation for the flight line as well as a reliable, resilient, efficient, and cyber secure microgrid backbone. Phase 2 of the project will provide an additional 4.6 MW of onsite generation. Phase 1 and Phase 2 combined will provide 100% of the flight line’s mission essential functions and critical installation services power in the event of a commercial power disruption. The onsite generation and controls included in this project will also address known vulnerabilities associated with inadequate onsite generation and fuel supplies, as defined in the IESP, and help mitigate the impacts of downtime from climate events, such as typhoons by generating power onsite. | [8 empty] | N/A | N/A | 43110 | N/A | N/A | N/A | ESPC + ERCIP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCAS Iwakuni | P-1019 | Microgrid and Backup Power, Phase 2 | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | Determine if Gov wants to start navigating ESPC + ERCIP |  | This project is the second phase of a two-phase ERCIP effort to enhance energy security for the MCAS Iwakuni flight line. Proposed construction in Phase 2 includes the following: a 4,600-kW gas-fired CHP unit, one 30,000 pounds per hour heat recovery steam generator, a gas compressor, associated mechanical and electrical work, utility interconnections, microgrid and other controls, commissioning, and cybersecurity. Supporting work includes site preparations, gas distribution piping, fiber/communication system extensions, and associated shipping/offloading costs for the equipment in Japan. The project is required to close IESP flight line vulnerabilities associated with inadequate generation and fuel delivery. The project also enhances energy security per Federal policy requirements and better positions MCIPAC to achieve General Berger’s (38th Commandant) objective to have stand-in fight capability at MCIPAC installations. | This project will enhance mission assurance and readiness by providing MCAS Iwakuni with 7.5 MW of onsite generation for the flight line as well as a reliable, resilient, efficient, and cyber secure microgrid backbone. Phase 2 of the project will provide an additional 4.6 MW of onsite generation. Phase 1 and Phase 2 combined will provide 100% of the flight line’s mission essential functions and critical installation services power in the event of a commercial power disruption. The onsite generation and controls included in this project will also address known vulnerabilities associated with inadequate onsite generation and fuel supplies, as defined in the IESP, and help mitigate the impacts of downtime from climate events, such as typhoons by generating power onsite. | [8 empty] | N/A | N/A | 40990 | N/A | N/A | N/A | ESPC + ERCIP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2025 | MCB Camp Lejeune | P-1568 | Water Resilience for Potable Water System | Submitted to OSD | No action until OSD selects FY25 projects in March 2025. | None |  | This project will install approximately 25 miles of potable and fire water lines at the following sites at Camp Lejeune: Industrial Area, Berkley Manor, Seth Williams Boulevard / Scout Hut Loop, Autumn Oval/Charles Street/Seth Williams Boulevard, and Marine Corps Air Station (MCAS) New River Enlisted Housing. The existing pipes are end of life, have leaks, and are at risk of catastrophic loss so will be abandoned in place. The project will also install a redundant water line from local utility to Midway Park. The project is required to increase the base's confidence in providing potable water to critical missions during normal and contingency operations. | This project will enhance mission assurance and support mission critical functions by improving base’s confidence in providing potable water to critical missions and housing areas by replacing over 25 miles of potable water lines throughout the base that are at end of life, starting to fail, and have unreliable water valves to allow systems to be isolated. This project will address known vulnerabilities associated with lack of a redundant water supply by building a new interconnection with the local water utility and by replacing piping systems that are failing. | [8 empty] | N/A | N/A | 70990 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCAGCC Twentynine Palms | P-MCIWEST-02 | 2021 NDAA Building 2080 Nanogrid with PV and BESS | Advanced Planning | Develop project | No action | None | This project will install PV and a BESS intended to largely take the Emergency Operations Center (EOC) and associated warehouse "off grid" and possibly make it "net zero". Initial calculations indicate that this project will allow the EOC to operate off commercial power grid by operating off the PV power during the day and the battery at night. The project is needed to close an IESP gap associated with inadequate power at this facility. | This project will enhance mission assurance and support mission critical functions by making the EOC and associated warehouse extremely resilient and capable of operating indefinitely with no concern for fuel. Should there be a situation in which the PV does not produce enough power to adequately recharge the battery, there is a generator that will run, but fuel consumption will be minimal, extending the operation of this facility essentially indefinitely. The project will address known vulnerabilities identified in the Installation Energy Security Plan about the resilience requirements for the EOC. | [8 empty] | N/A | N/A | 4000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCAS Cherry Point | P-266 | Steam Decentralization | Advanced Planning | Develop project | No action | None | This project will demolition steam and condensate lines serving nine non-critical facilities along Sixth Avenue at Cherry Point and install local energy-efficient boilers and hot water heaters. The project is needed to ensure that critical buildings served by the steam plant have an adequate and reliable source of steam to conduct daily operations. Decentralizing a few facilities on the existing steam system was determined to be the most efficient way to ensure adequate steam is delivered to critical missions. | This project will enhance mission assurance and support mission critical functions by decentralizing non-critical facilities from the steam system and prioritizing steam delivery to mission critical facilities, including the Second Marine Aircraft Wing (2nd MAW), Fleet Readiness Center East (FRCE), Combat Logistics Command 21 (CLC-21) of the Second Marine Logistics Group (2nd MLG), and the Center for Naval Aviation Technical Training (CNATT). Redirecting steam loads from non-industrial areas improves reliability of steam plant to supply steam processes required for these critical aircraft maintenance and industrial facilities. This project reduces vulnerabilities associated with maintaining steam lines to non-critical facilities. For instance, steam decentralization efforts will remove the resource burden of maintaining large sections of aging steam and condensate lines to Sixth Avenue facilities, allowing those resources to be redirected to critical mission infrastructure. | [8 empty] | N/A | N/A | 5566 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCAS Yuma | P-MCIWEST-03 | Redundant Electric Supply, Airport Control Tower | Advanced Planning | Develop project | No action | None | This project will add an electrical distribution circuit as a secondary supply to the Airport Control Tower. This project is required to provide the required level of resilience to the control tower and close a gap identified in the Installation Energy Security Plan. | This project will enhance mission assurance and support mission critical functions by providing the Airport Control Tower, a critical building supporting mission essential functions at MCAS Yuma, with a more reliable and resilient power source. This project addresses the known vulnerability that having only one power supply is a significant risk since a power loss stops all essential/critical aviation operations on the base. | [8 empty] | 3 | N/A | 10000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCAS Cherry Point | P-267 | Energy Management Control System | Advanced Planning | Develop project | No action | None | This project will modernize, expand, and cyber secure the existing energy management control system (EMCS) at 126 buildings, including multiple critical facilities that support mission essential functions and critical installation services. The project will modernize approximately 55 Network Automation Engines (NAE) with the latest Supervisory Network Engines (SNE), install approximately 3,750 building level controllers, repair communication buses, convert outdated communication bus protocol to current industry standard (BACnet), provide Open Blue Enterprise Manager (OBEM) software package for Artificial Intelligence (AI) driven system monitoring and reporting, and install 133 Tempered Air Zero Trust devices at SNE level and 67 Nozomi Guardian devices at EMCS network for continuous security monitoring. The project also will evaluate the use of GovCloud to host OBEM for super computing power. This project is required to maximize asset lifecycle/efficiency, streamline workforce production, and support deployment of resilience strategies to optimize energy consumption in critical facilities. Zero trust principles will provide uncompromised security on the EMCS network for critical infrastructure. | The project will enhance mission assurance and support mission critical functions by providing a centralized Energy Management Control System for 126 buildings, including multiple critical facilities supporting Second Marine Aircraft Wing (2nd MAW), Fleet Readiness Center East (FRCE), Combat Logistics Command 21 (CLC-21) of the Second Marine Logistics Group (2nd MLG), and the Center for Naval Aviation Technical Training (CNATT). The project mitigates known vulnerabilities identified in the Installation Energy Security Plan with the Energy Management Control System and its cybersecurity. | [8 empty] | N/A | N/A | 26900 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCAS Yuma | P-MCIWEST-04 | Microgrid and Backup Power, Cannon Air Defense Complex (CADC) | Advanced Planning | Develop project | No action | None | This project will construct a microgrid at CADC, an area geographically separate from the main installation that supports critical training functions. The project is required to address multiple Installation Energy Security Plan gaps related to inadequate electrical systems and backup power for critical missions in this area. | This project will enhance mission assurance and support mission critical functions by providing CADC with a reliable, resilient, and efficient microgrid that will enable CADC, which supports the largest training range in USMC and hosts some of the largest aviation and other essential training activities for the DoD, to continue operations regardless of the state of the electric power grid. This project addresses known vulnerabilities associated with military training impacts if power is lost to the area and closes Installation Energy Security Plan gaps. | [8 empty] | N/A | N/A | 15000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCLB Albany | P-MCLBA-1 | Battery Energy Storage System | Advanced Planning | Develop project | No action | None | This project will provision and install 50 MWs of battery energy storage systems for the existing 3MW solar farm. Georgia Power Corp. (GPC) received permission from the Georgia PUC to install 88 MW's of solar battery storage on its grid. MCLBA has top priority customer position with GPC for installation. The project is needed to be able to use the renewable energy during a power disruption. | The project enhances mission and assurance and supports mission critical facilities by providing MCLBA with a more robust energy system that will help maximize energy availability through the use of BESSs. The project addresses known vulnerabilities associated with the 3 MW solar farm energy system not being able to be utilized during power outages due to the lack of BESSs. | [8 empty] | N/A | N/A | 3000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCB Camp Pendleton | P-MCIWEST-05 | Generator Quick Connects | Advanced Planning | Develop project | No action | None | This project will install universal connection points with 'break then make' manual transfer switches (MTSs) at 20 12kV/480V transformers to allow portable backup generators to be connected to the transformer and power multiple facilities during an outage. This project is needed to provide an option to provide backup power to facilities that may need backup power during an extended outage. This project is required to close Installation Energy Security Plan gaps associated with inadequate backup power for critical buildings that support mission essential functions, critical installation services, or continuity of operation plans. | This project will enhance mission assurance and support mission critical functions by ensuring the base has the option of providing backup power to these facilities in the event of a commercial power outage. The project addresses known vulnerabilities associated with inadequate onsite generation throughout MCB Camp Pendleton. | [8 empty] | N/A | N/A | 1500 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCB Camp Lejeune | P-1573 | Domestic Water System | Advanced Planning | Develop project | No action | None | This project will modernize the domestic water system by replacing the piping system, upgrading the pumping system and its controls, and addressing potable water treatment deficiencies, and installing reclaimed water systems. This project will focus on replacing three sections of water main in Berkley Manor area as well as provide an emergency water connection to the Onslow Water and Sewer Authority at Midway Park. The project is required to address water system deficiencies. | This project will enhance mission assurance and support mission critical functions by providing a more reliable, resilient, and efficient water system to serve critical buildings. It addresses known vulnerabilities associated with aged piping systems and water waste. | [8 empty] | N/A | N/A | 34000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCAGCC Twentynine Palms | P-MCIWEST-06 | Cogeneration Plant Capacity Expansion | Advanced Planning | Develop project | No action | None | This project will repair and add capacity to Cogeneration Plant 2. This work is required to correct current capacity issues and allow additional buildings to be added to the distribution network. The work will help mitigate energy security gaps identified in the Installation Energy Security Plan. | This project will enhance mission assurance and support mission critical functions by providing a more reliable and efficient onsite generation asset to provide power, heat, and cooling to critical buildings aboard the installation. The project will mitigate vulnerabilities identified in the Installation Energy Security Plan. | [8 empty] | N/A | N/A | 10000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCLB Albany | P-987 | Electrification with HVAC Upgrade | Advanced Planning | Develop project | No action | None | This project electrifies the HVAC system in building 3500 by replacing gas-fired steam boilers with completely electric ground source heat pump systems and installing new cooling systems, distribution equipment, and controls. The project is required to support compliance with Executive Order 14057 Catalyzing Clean Energy Industries and Jobs Through Federal Sustainability (8 December 2021) which targets net-zero Federal buildings by 2045 through reduction of Scope 1 and Scope 2 greenhouse gas emissions through energy conservation measures and electrification. Electrification of the Building 3500 HVAC systems will contribute to both energy savings and reduction of greenhouse gas emissions. | This project enhances mission and assurance and supports mission critical facilities by providing a critical building supporting mission essential functions with a reliable ground source heat pump system and supporting HVAC system. The project addresses known vulnerabilities associated with greenhouse gases and climate change by using the GSHP to concentrate naturally existing heat, rather than by producing heat through the combustion of fossil fuels. | [8 empty] | N/A | N/A | 15000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCLB Barstow | P-MCIWEST-07 | Electrical Substation and Circuits | Advanced Planning | Develop project | No action | None | This project will modernize the installations two main substations as well as the electrical circuits departing these substations. This work is required because the existing infrastructure uses old technology and is at end of life. The project will set the stage for a microgrid that is in the early stages of development. The project is also required to address energy security gaps identified in the Installation Energy Security Plan related to the electrical system. | This project will enhance mission assurance and support mission critical functions by modernizing the electrical system that provides power to critical missions aboard the base. The project addresses multiple known electric vulnerabilities identified in the Installation Energy Security Plan. | [8 empty] | N/A | N/A | 10000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCB Camp Lejeune | P-1569 | Electrical Distribution System, Phase 1 | Advanced Planning | Develop project | No action | None | This project will provide electrical grid resilience in the Paradise Point area of MCB Camp Lejeune by converting overhead lines to underground, installing loop feeds, installation additional substation feeders, and modernizing the SCADA system. The project also will provide cybersecurity. The project is required to close Installation Energy Security Plan gaps associated with electrical system and SCADA system deficiencies. | This project will enhance mission assurance and support mission critical functions by increasing energy availability of the electrical distribution system serving Paradise Point. The project addresses known vulnerabilities identified in the Installation Energy Security Plan associated with electrical system, SCADA system, and cybersecurity deficiencies. | [8 empty] | N/A | N/A | 34400 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCB Camp Lejeune | P-1570 | Electrical Distribution System, Phase 2 | Advanced Planning | Develop project | No action | None | This project will provide electrical grid resilience in the Courthouse Bay, Onslow Beach, and housing areas of MCB Camp Lejeune by converting overhead lines to underground, installing loop feeds, installation additional substation feeders, and modernizing the SCADA system. The project will include reconductoring the area and providing an alternate feed to the hospital. The project also will provide cybersecurity. The project is required to close Installation Energy Security Plan gaps associated with electrical system and SCADA system deficiencies. | This project will enhance mission assurance and support mission critical functions by increasing energy availability of the electrical distribution system serving Courthouse Bay, Onslow Beach, and nearby housing areas. The project addresses known vulnerabilities identified in the Installation Energy Security Plan associated with electrical system, SCADA system, and cybersecurity deficiencies. | [8 empty] | N/A | N/A | 22400 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2026 | MCB Camp Lejeune | P-1571 | Electrical Resilience Measures, Phase 3 | Advanced Planning | Develop project | No action | None | This project will provide electrical grid resilience in the MCAS New River area of MCB Camp Lejeune by converting overhead lines to underground, installing loop feeds, installation additional substation feeders, and modernizing the SCADA system. The project also will provide cybersecurity. The project is required to close Installation Energy Security Plan gaps associated with electrical system and SCADA system deficiencies. | This project will enhance mission assurance and support mission critical functions by increasing energy availability of the electrical distribution system serving MCAS New River. The project addresses known vulnerabilities identified in the Installation Energy Security Plan associated with electrical system, SCADA system, and cybersecurity deficiencies. | [8 empty] | N/A | N/A | 14100 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Pendleton | P-MCIWEST-08 | Electric Vehicle Supply Equipment | Advanced Planning | Develop project | No action | None | This project will install new bi-directional charging stations basewide and modernize existing charging stations. The project is required to support the Administration's objectives to electrify the vehicle fleet. | This project will not directly enhance mission assurance or support mission critical functions; however, it will support the Administration's objectives to electrify the vehicle fleet. The project will address known vulnerabilities about not having adequate EVSE infrastructure to support the forthcoming fleet. | [8 empty] | N/A | N/A | 1500 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Lejeune | P-1572 | Electrical Resilience Measures, Phase 4 | Advanced Planning | Develop project | No action | None | This project will provide electrical grid resilience in various/miscellaneous areas of MCB Camp Lejeune by converting overhead lines to underground, installing loop feeds, installation additional substation feeders, and modernizing the SCADA system. The project also will provide cybersecurity. The project is required to close Installation Energy Security Plan gaps associated with electrical system and SCADA system deficiencies. | This project will enhance mission assurance and support mission critical functions by increasing energy availability of the electrical distribution system serving miscellaneous segments of the electrical system throughout the installation. The project addresses known vulnerabilities identified in the Installation Energy Security Plan associated with electrical system, SCADA system, and cybersecurity deficiencies. | [8 empty] | N/A | N/A | 24700 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Pendleton | P-MCIWEST-09 | Microgrid and Backup Power | Advanced Planning | Develop project | No action | None | This project will build a microgrid with backup power at Area 43 by installing approximately 18+ MW of onsite generation and storage conventional, solar photovoltaic, and battery energy storage systems. Where needed, conventional generators will be equipped by dual fuel capability. | This project will enhance mission assurance and support mission critical functions by ensuring all mission critical facilities in Area 43 have adequate reliable, resilient, and efficient backup power so that missions can continue regardless of the state of the electric power system. The project will address multiple energy security gaps in Area 43 identified in the Installation Energy Security Plan. | [8 empty] | N/A | N/A | 55000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Lejeune | P-CAMLEJ-1 | Dual Fuel Generator Conversion | Advanced Planning | Develop project | No action | None | This project will convert critical infrastructure diesel generators at Camp Lejeune to natural gas combustion systems to provide reduced energy costs, increased reliability, diversify fuel sources, and conform to the 14 day outage resilience mandate. The project is required to enhance resilience and close Installation Energy Security Plan gaps. | This project will enhance mission assurance and support mission critical functions by decreasing reliance and delivery limitations of diesel fuel for electric generators. This project will address known vulnerabilities identified in the Installation Energy Security Plan associated with the goal to be able to operate generators continuously during a 14-day contingency event. | [8 empty] | N/A | N/A | 18000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Pendleton | P-MCIWEST-10 | Solar PV and Backup Generator Monitoring | Advanced Planning | Develop project | No action | None | This project will install monitoring and/or control devices on existing solar photovoltaic and backup generators so that the systems can be centrally monitored and/or controlled in the base's energy management command center. Data such as run time of back up generators, real time emissions, generation of PV assets will be available. This project is needed to better monitor and control onsite generations assets aboard the installation, help reduce notices of violation (NOVs) related to CA mandated Air Permit limitations for back up generators, and ensure that back up generators and solar PV systems are properly functioning. Cybersecurity will also be provided. | This project will enhance mission assurance and support mission critical functions by providing additional information about the loads on backup generation assets on critical facilities and by cybersecuring the monitoring/control devices for these systems. The project will address known vulnerabilities associated with onsite generation asset performance by providing data to help diagnose operational problems. | [8 empty] | N/A | N/A | 10000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Lejeune | P-CAMLEJ-2 | Fuel Cell Generator | Advanced Planning | Develop project | No action | None | This project will install a small scale fuel cell generating system. The project is needed to enhance resilience. It is a small scale pilot project intended to evaluate the benefits of using fuel cells to support critical power backup requirements. | This project will enhance mission assurance and support mission critical functions by providing a critical facility with a fuel cell generator as the primary backup power source. The project will address known vulnerabilities associated with inadequate backup power at a critical facility. | [8 empty] | N/A | N/A | 20000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCLB Albany | P-MCLBA-2 | BEQ Domestic Hot Water Heating Modifications | Advanced Planning | Develop project | No action | None | This project will modify the barracks domestic hot water system to maximize the benefits of the solar collection system. The modification to include repairing and replacing existing equipment, components and piping and a circulation pump to circulate water through the solar drain back tank and to the hot water storage tank. A water softening system will be installed in addition to building management system controller to monitor, control and trend the operation of the solar and boiler heating system. The project is needed to reduce energy consumption and emissions in accordance with Federal energy requirements. | The project enhances mission and assurance and supports mission critical facilities by providing MCLBA barracks with a more reliable hot water heating system. The project addresses known vulnerabilities associated with needing to reduce greenhouse gas emissions to mitigate climate change by using solar hot water systems instead of electric or gas-consuming hot water heaters. | [8 empty] | N/A | N/A | 5000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCLB Albany | P-MCLBA-3 | Grounds Source Heat Pump Borehole Thermal Energy Storage System | Advanced Planning | Develop project | No action | None | This project will provide operational adjustments and upgrades to the existing Ground Source Heat Pump (GSHP) Borehole Thermal Energy Systems (BTES) installed at 11 buildings. The project is required to enhance current the energy performance of the buildings and meet federal energy consumption reduction, electrification, and clean energy requirements. | The project will enhance mission assurance and support mission critical function by providing critical facilities supporting mission essential functions with a more reliable HVAC system by repairing aged systems and providing thermal energy storage. The project will address known vulnerabilities associated with greenhouse gases and climate change by using the GSHP BTES to concentrate and store naturally existing heat, rather than by producing heat through the combustion of fossil fuels. | [8 empty] | N/A | N/A | 1500 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCLB Albany | P-MCLBA-4 | Solar Photovoltaic System Canopy | Advanced Planning | Develop project | No action | None | MCLBA requires this project to provision and install a solar photovoltaic system Canopy for Production Plant Albany. The project is required to increase onsite renewable energy production and support compliance with Federal energy requirements. | The project will enhance mission assurance and support mission critical facilities by providing a structure to store refurbished vehicles and equipment that is protected from the elements. The project will help reduce maintenance rework due to equipment being exposed to the elements in the harsh Albany humidity and heat. The project will address known vulnerabilities associated with greenhouse gases and climate change by increasing onsite renewable energy production. | [8 empty] | N/A | N/A | 3500 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCLB Albany | P-MCLBA-5 | Electrical Interconnect to Existing 31 MW EUL | Advanced Planning | Develop project | No action | None | This project will install electrical infrastructure and equipment to allow MCLB Albany to consume power from the GPC 31 MW solar array that was installed via an EUL. This project is needed because the base does not currently have the ability to use this power. | This project will enhance mission assurance and support mission critical functions by providing access to additional onsite power generation resources in the event of a power disruption. It addresses known vulnerabilities associated with not being able to leverage | [8 empty] | N/A | N/A | 7000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2027 | MCB Camp Lejeune | P-CAMLEJ-3 | Microgrid and Backup Power, MCAS New River | Advanced Planning | Develop project | No action | None | This project will install a microgrid with backup power at MCAS New River to service critical flight line and other aviation readiness facilities. Backup power systems will include a combination of conventional energy generation, renewable energy generation, and storage. The project is required to close Installation Energy Security Plan gaps associated with backup power requirements for critical facilities. | This project will enhance mission assurance and support mission critical functions by building a microgrid with backup power at the air station. The project will address known vulnerabilities associated with inadequate backup power at a critical facilities. | [8 empty] | N/A | N/A | 27000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2028 | MCAS Yuma | P-MCIWEST-12 | Electric Distribution System | Advanced Planning | Develop project | No action | None | This project will modernize MCAS Yuma's electrical distribution grid components that have reached or exceeded the statistical service life. This project is required to address energy security gaps defined in the Installation Energy Security Plan. The project is also required to improve the Station's ability to avoid, minimize, and recover from electrical outages. This is important for the mission because MCAS aviation training and other missions rely on a reliable and resilient electrical power system. | This project will enhance mission assurance and support mission critical functions by modernizing the electrical distribution system to improve the reliability and resilience of the system and increase SAIFI and SAIDI metrics. Improvements to electric system are necessary to ensure that critical missions aboard the Station have adequate energy availability. The project will address known vulnerabilities with the aged electrical system as well as provide climate resilience by building onsite infrastructure that will facilitate the future installation of a microgrid, so that the Station does not have to rely on the commercial utility for power as the demand for power gets greater with increasing temperatures and more severe climatic events. | [8 empty] | N/A | N/A | 25000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2028 | MCB Camp Lejeune | P-CAMLEJ-4 | Microgrid and Backup Power, Hospital and Water Treatment Plant | Advanced Planning | Develop project | No action | None | This project will install a microgrid with backup power to serve the hospital and water treatment plant. Backup power systems will include a combination of conventional energy generation, renewable energy generation, and storage. The project is required to close Installation Energy Security Plan gaps associated with backup power requirements for critical facilities. | This project will enhance mission assurance and support mission critical functions by building a microgrid with backup power to serve critical facilities, including the hospital and water treatment plant. The project will address known vulnerabilities associated with inadequate backup power at a critical facilities. | [8 empty] | N/A | N/A | 20000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2028 | MCAGCC Twentynine Palms | P-MCIWEST-13 | Chilled Water Loop Extension | Advanced Planning | Develop project | No action | None | This project will extend the chilled water loop to several buildings not currently served by the central chilled water system. This will facilitate energy consumption reduction by increasing the cogeneration plant efficiency and decreasing energy consumption at buildings currently served by independent chillers. This project is required to reduce energy use intensity. | This project will enhance mission assurance and support mission critical functions by ensuring critical facilities have a reliable source for cooling. The project will reduce educe vulnerabilities identified in the Installation Energy Security Plan associated with energy consumption reduction. | [8 empty] | N/A | N/A | 4000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2028 | MCB Camp Lejeune | P-CAMLEJ-5 | Microgrid and Backup Power, Substation 1 | Advanced Planning | Develop project | No action | None | This project will install a microgrid with backup power at Substation 1 to serve Marine Expeditionary Force Headquarters, Bachelor Enlisted Quarters, and Air Naval Gunfire Liaison Company (ANGLICO). Backup power systems will include a combination of conventional energy generation, renewable energy generation, and storage. The project is required to close Installation Energy Security Plan gaps associated with backup power requirements for critical facilities. | This project will enhance mission assurance and support mission critical functions by building a microgrid with backup power to serve critical facilities connected to Substation 1 during normal and contingency operations. Numerous installation and MCIEAST commands and critical facilities are served by this substation. The project will address known vulnerabilities associated with inadequate backup power at a critical facilities. | [8 empty] | N/A | N/A | 25000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2028 | MCAGCC Twentynine Palms | P-MCIWEST-14 | Lighting Replacement | Advanced Planning | Develop project | No action | None | This project will upgrade old, outdated, inefficient exterior and interior lighting systems with LEDs. The project is required to reduce energy use intensity, improve safety and security, and provide better working conditions for Marines and civilians aboard MCAGCC. | This project will enhance mission assurance and support mission critical functions by reducing energy demand and consumption and by providing improved safety, security, and working conditions for Marines and civilians. The project will reduce vulnerabilities identified in the Installation Energy Security Plan associated with energy consumption reduction. | [8 empty] | N/A | N/A | 3000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2028 | MCB Camp Lejeune | P-CAMLEJ-6 | Microgrid and Backup Power, Stone Bay | Advanced Planning | Develop project | No action | None | This project will install a microgrid with approximately 5 MW of backup power/storage at Stone Bay. Backup power systems will include a combination of conventional energy generation, renewable energy generation, and storage. The system will be connected to the Rifle Range feeder and the MARSOC feeder with added controls on the normally open connection between the two. The project is required to close Installation Energy Security Plan gaps associated with backup power requirements for critical facilities. | This project will enhance mission assurance and support mission critical functions by building a microgrid with backup power at Stone Bay. The project will address known vulnerabilities associated with inadequate backup power at a critical facilities. | [8 empty] | N/A | N/A | 26000 | N/A | N/A | N/A | Design/Build | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Note on F2: Kim, Irwin: The definitions below describe the various stages an ERCIP project goes through from cradle (i.e., planning) to grave (i.e., canceled, completed, or decommissioned). Proposed: Default project status that begins upon creation of a new ECIP project. These projects are proposed by the services for consideration in the ECIP Annual Budget. Budgeted: Projects are selected for inclusion in the ERCIP President’s Budget that is sent to Congress. This is only a budget assignment, actual funds have not yet been received or provided to the Components. Authorized: Status used for projects that were authorized in a National Defense Authorization Act (NDAA), whether lump sum (FY20 and earlier) or specified (FY21 and later). Appropriated: Status used for projects that were appropriated funds in an appropriations act. Enacted: Refers to an ERCIP construction project that has been authorized in an NDAA and appropriated funds in an appropriations act. P&D Distributed: Reflects the amount of funds issued via a funding document by the OSD Comptroller to a Component to provide design funds for planning and design of ERCIP construction projects. Awarded: Indicates that the funds for the project are obligated against a design or construction contract vehicle. Delayed: Refers to a completion date that has slipped to the right from the original design or construction estimated completion date (ECD), or from a previously documented, delayed completion date. Under Construction: Designates projects that are currently in the construction phase. The project is not yet on-line and is not generating any savings or producing energy Complete / Operational: Construction is complete, and the project is operational, generating energy/water savings or producing energy. Canceled: Funds allocated for this project are revoked. No portion of the project was implemented or some design or construction funds were expended, but the project did not proceed. Decommissioned: The project was operational for a period of time, generating energy/water saving or producing energy. The project reached the end of its lifecycle and was taken off line.
Note on V2: Kim, Irwin: 1. How much was project originally programmed for. 2. How much was approved by OSD for us to use? Includes any change requests approved by OSD. 3. Current working estimate 4. Source of CWE NEED TO SHOW A PROCESS. NEED TO UNDERSTAND OSD RULES. Separate sequence to show P&D progression. Need to have ledge show where we spent construction and P&D funds. How much P&D funding is available. Need to review w/ Capt Altman where our ledger shows we spent money and confirm.
Note on AK2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Turnover to Project Sponsor
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LE12E600M
Note on W8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Best guess
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MI0984R
Note on D16: PE1292M
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously Construct Solar Sun Shades with Energy Storage

## ESPC-UESC
[5 empty] | Last Updated: | 2022-12-27 | [6 empty] | 162540897.373 | Last Updated: 11/15/2022 |  |  |  |  | Milestone Dates
Fiscal Year of Award | Installation | Project Title | Type | Status | Next Steps | MCICOM GF-PW Action | Notes | Project Description | Mission Alignment | Current PP Year | Payment to NAVFAC Due (FY2023) | Payment to Contractor Due | Payment Amount Due | Payment Status | Notes | Contractor | Contract # | Delivery Order | Installation Request Letter Date | Region Endorsement Letter Date | MCICOM Approval Letter Date | J&A Date (for UESC) Acquisition Contractor Selection Date (ESPC) | PA Start | PA Complete | IGA Start | IGA Complete | Award Date | Construction Start | Construction Complete | PP Start Date (First Payment Year) | PP Last Payment Date | Calculated Contract Term (Yrs) | First Implementation Price | First Cost | Total TPF Cost | Remaining Balance (Start of FY)
2000 | MCAGCC 29 Palms | MCAGCC 29 Palms, ESPC, JCI, 1 | ESPC | Complete |  |  |  | Installed high efficiency chiller |  | N/A | N/A | Contract Complete | N/A | N/A |  | JCI | DACA87-97-D-0069 | 1 | [8 empty] | 2000-08-14 |  |  | 2001-10-01 | 2017-09-30 | 17.1397 | 2279818 |  | 7144569 | Complete
2001 | MCAS Miramar | MCAS Miramar, ESPC, Noresco, 1 | ESPC | Complete |  |  |  | *Thermal energy storage (TES) and centralized chiller plant for flight simulator building, ltg upgrades, daylight controls |  | N/A | N/A | Contract Complete | N/A | N/A |  | Noresco | N47408-01-F-4710 | 1 | [8 empty] | 2001-09-26 |  |  | 2007-02-26 | 2019-02-25 | 17.4274 | 2924540 |  | 8760029 | Complete
2001 | MCAS Beaufort | MCAS Beaufort, ESPC, Trane, 1 & 2 | ESPC | Complete |  |  |  | GSHPs, lighting retrofits, and motor & drive upgrades in 35 Shore Buildings. GSHP at Buildings 405, 614, 703, 807, 1039 and 1078. Building automation, lighting, water, pump energy, 750-ton central chiller plant and (15) 100 kW micro-turbines. |  | N/A | N/A | Contract Complete | N/A | N/A |  | Trane | N47408-01-F-4713 | 1 & 2 | [8 empty] | 2001-09-28 |  |  | 2006-01-01 | 2019-08-31 | 17.9342 | 23450821 |  | 32156276 | Complete
2006 | MCAS Miramar | MCAS Miramar, ESPC, Noresco, 2 | ESPC | Complete |  |  |  | Lighting in Bldg 7209; card reader HVAC controls for Building 4325. |  | N/A | N/A | Contract Complete | N/A | N/A |  | Noresco | N62473-06-F-3039 | 2 | [8 empty] | 2006-04-11 |  |  | 2007-02-26 | 2019-02-25 | 12.8849 | 1570800 |  | 2571448 | Complete
2006 | MCB Quantico | MCB Quantico, ESPC, Ameresco, 2 | ESPC | Complete |  |  |  | Improve safety and reduce energy use/costs by installing high efficiency ltg fixtures and controls |  | 14 | N/A | Contract Complete | N/A | N/A |  | Ameresco | N62473-06-F-3050 | 2 | [8 empty] | 2006-05-12 |  |  | 2007-07-27 | 2021-07-26 | 15.2164 | 4629791 |  | 7388272 | Complete
TBD | MCB Camp Lejeune | MCB Camp Lejeune, ESPC, Unknown, 1 | ESPC | Complete |  |  |  | Ltg in 91 buildings at Camp Johnson, Courthouse Bay, Amphibious, and New River Air Station. |  | N/A | N/A | Contract Complete | N/A | N/A |  | Unknown | Unknown | 1 | [8 empty] | Unknown |  |  | Unknown | 2019 | Unknown | 2562666 |  | 4151426 | Complete
TBD | MCAS Camp Pendleton | MCAS Camp Pendleton, ESPC, Noresco, 1 | ESPC | Complete |  |  |  | Lighting and controls; DDC for 22 bldgs; HVAC in 6 bldgs |  | N/A | N/A | Contract Complete | N/A | N/A |  | Noresco | N47408-03-F-5268 | 1 | [8 empty] | Unknown |  |  | Unknown | 2019 | Unknown | 1405846 |  | 15227276 | Complete
2002 | MCB Quantico | MCB Quantico, ESPC, Ameresco, 1 | ESPC | PP | Start determining path forward post PP. This includes developing a plan to address boiler maintenance and determing what will be done with propane air system. | None | None | Improve reliability and resilience of heating systems and reduce GHG emissions by decentralizing an aged coal-fired steam plant and installing a contractor owned/operated natural gas system with a propane-air mixing facility as redundant fuel source. |  | 19 OF 23 | 2022-07-18 | 2022-10-01 | 5691124 | PAST DUE; PAYMENT IN PROGRESS. Funds sent to EXWC 10/17/22; Funds accepted by EXWC 10/21/2022. Pending mod issuance. |  | Ameresco | N47408-02-F-4965 | 1 | [8 empty] | 2002-09-30 |  |  | 2004-10-01 | 2027-09-30 | 25.0164 | 28286845 | 28286845 | 121072595 | 29702660
2003 | MCLB Albany | MCLB Albany, ESPC, ESG, 1 | ESPC | PP | End PP | Recommend inquiring about OMRR post PP. | None | Reduce energy use/costs by installing GSHPs, optimizing industrial compressed air system, and repairing HVAC systems |  | 19 OF 19 | 2022-09-17 | 2022-12-01 | 1570553 | PAYMENT IN PROGRESS – EXWC requested funds on 10/14/22. |  | ESG | N47408-03-F-5305 | 1 | [8 empty] | 2003-09-29 |  |  | 2004-12-01 | 2023-11-30 | 20.1836 | 14167067 | 14167067 | 31701548 | 1570553
2001 | MCAGCC 29 Palms | MCAGCC 29 Palms, ESPC, JCI, 2 & 3 | ESPC | PP | None | Recommend inquiring about OMRR post PP. | None | Mitigates critical electrical vulnerabilities associated with reliance on commercial power and reduced energy consumption/costs with cogeneration plant |  | 19 OF 21 | 2022-09-17 | 2022-12-01 | 9168986 | PAYMENT IN PROGRESS - EXWC requested funds on 10/14/22. MCAGCC sent funds on 11/7/22. |  | JCI | DACA87-97-D-0069-EJP3 | 2 & 3 | [8 empty] | 2001-09-30 |  |  | 2004-12-01 | 2025-07-30 | 23.8466 | 75678746 | 75678746 | 186268118 | 25919226
2016 | MCLB Albany | MCLB Albany, ESPC, Constellation, 3 | ESPC | PP | REAs. See payment status (column N) | Recommend inquiring about regulary status updates for Requests for Equitable Adjustment. | None | Second ESPC aimed at achieving net zero by installing a second landfill gas generator, smart grid controls, and a steam turbine that uses waste steam from neighboring 50 MW industrial biomass plant |  | 3 OF 21 (theoretically) | 2022-11-18 | 2023-02-01 | 5636363 | FUTURE PAYMENT – Performance period modification was made on 10/19/22. | The schedule provided is what EXWC is currently tracking; however, there are notes at the bottom of the TO schedule about various payments so actuals may vary based on closeout schedule. The USMC has obligated some payments but NAVFAC has not paid the contractor since construction is not complete. | Constellation | N39430-16-F-1838 | 3 | [8 empty] | 2016-09-30 |  |  | 2018-09-30 | 2041-09-30 | 25.0164 | 50318691 | 50318691 | 163373537 | 144242354
2017 | MCLB Barstow | MCLB Barstow, ESPC, ESG, 1 | ESPC | PP | See payment status (column N) | None | None | Improved quality of life and safety for Marines, increased renewable energy production, and drove down energy/water use/costs by installing solar pv and retrofitting water and ltg systems |  | 5 OF 22 | 2023-01-16 | 2023-04-01 | 940021 | FUTURE PAYMENT |  | ESG | N39430-17-F-1995 | 1 | [8 empty] | 2017-09-28 |  |  | 2019-04-01 | 2041-03-31 | 23.5205 | 11397830 | 11397830 | 25023488 | 21285113
2010 | MCLB Albany | MCLB Albany, ESPC, Chevron, 2 | ESPC | PP | See payment status (column N) | None | None | First ESPC aimed at achieving net zero base by installing a landfill gas cogeneration system |  | 13 OF 22 | 2023-03-18 | 2023-06-01 | 2984110 | FUTURE PAYMENT |  | Chevron | N62583-10-F-0311 | 2 | [8 empty] | 2009-12-18 |  |  | 2011-07-01 | 2033-04-30 | 23.3808 | 20460945 | 20460945 | 63877110 | 35550480
2017 | MCRD Parris Island | MCRD Parris Island, ESPC, Ameresco, 1 | ESPC | PP | See payment status (column N) | None | None | Provides capability to operate base for 21+ days without commercial power via installation-wide smart grid with cogeneration, solar pv, batteries, and controls |  | 5 OF 23 | 2023-03-18 | 2023-06-01 | 7567355 | FUTURE PAYMENT |  | Ameresco | N39430-17-F-1901 | 1 | [8 empty] | 2016-12-28 |  |  | 2019-06-01 | 2041-11-30 | 24.9397 | 101636480 | 101636480 | 210617737 | 177641727
2008 | MCB Hawaii | MCB Hawaii, ESPC, Noresco, 1 | ESPC | PP | See payment status (column N) | None | MCB would like to pay this off if MCICOM has funding to do so. | Modernize aged building systems, reduce energy consumption/costs, and improve quality of life for Marines by replacing HVAC and ltg systems |  | 15 OF 21 | 2023-05-18 | 2023-08-01 | 1432517 | FUTURE PAYMENT |  | Noresco | N62583-08-F-0029 | 1 | [8 empty] | 2008-03-04 |  |  | 2010-08-01 | 2030-07-31 | 22.4219 | 14488224 | 14488224 | 28107687 | 10411665
2009 | MCAS Beaufort | MCAS Beaufort, ESPC, Trane, 3 | ESPC | PP | See payment status (column N) | None | None | Build-out central EMCS to improve reliability and efficiency of building HVAC systems and reduce energy use/costs by replacing chillers and installing GSHPs and new ltg systems |  | 14 OF 18 | 2023-05-18 | 2023-08-01 | 426930 | FUTURE PAYMENT |  | Trane | N62583-09-F-0105 | 3 | [8 empty] | 2009-07-31 |  |  | 2010-08-31 | 2028-08-31 | 19.0986 | 4975307 | 4975307 | 8314957 | 2001716
2016 | MCAS Beaufort | MCAS Beaufort, ESPC, Woodstone, (ENABLE) | ESPC | PP | See payment status (column N) | None | None | Improve safety and reduce energy use/costs through interior and exterior ltg system upgrades, to include airfield lighting |  | 7 OF 12 | 2023-06-18 | 2023-09-01 | 476450 | FUTURE PAYMENT |  | Woodstone | N39430-16-F-1884 | (ENABLE) | [8 empty] | 2016-09-30 |  |  | 2017-11-01 | 2029-10-31 | 13.0932 | 6393912 | 6393912 | 7521972 | 2850529
2013 | MCB Camp Pendleton | MCB Camp Pendleton, UESC, SDG&E, 20 | UESC | PP | None | None | None | Expand FRCS capabilities by repairing DDCs and reduce energy use/costs with boiler and ltg replacements |  | 9 OF 14 | N/A | 2022-10-01 | 133496 | PAID ON TIME using FY22 funds in SEP 2022 |  | SDG&E | N62473-13-G-1403 DO #0002 | 20 | [8 empty] | 2013-09-23 |  |  | 2014-10-01 | 2027-10-01 | 14.0301 | 1374730 | 1374730 | 1868945.26 | 800976
2017 | MCRD San Diego | MCRD San Diego, UESC, SDG&E, 6 | UESC | PP | None | None | None | Improve safety by replacing inefficient and failing interior and exterior ltg systems with LED fixtures |  | 5 OF 8 | N/A | 2022-10-01 | 230125 | PAID ON TIME using FY22 funds in SEP 2022 |  | SDG&E | N62473-13-G-1403 DO# 0005 | 6 | [8 empty] | 2017-09-27 |  |  | 2017-09-27 | 2025-10-01 | 8.0164 | 1515354 | 1515354 | 1760409.93 | 839909.93
2019 | MCB Camp Lejeune | MCB Camp Lejeune, UESC, Duke Energy, 2 | UESC | PP | None | None | None | Improve reliability of aged electrical and ltg systems by replacing and modernizing aged substations, repairing PV and metering systems, and replacing airfield ltg |  | 3 OF 21 |  | 2022-12-01 | 920559.03 | PENDING PAYMENT upon ECM 7B completion: $298,080.10 (TO2). Note: Modification payments are being paid by installation as construction work is completed. | - TO2M6: Obligated/Awarded 9/28, IAO $622,478.93; Due 1 November 2022 - TO2: $298,080.10, due on receipt of ECM 7B, Expected December 2022 | Duke Energy | N40085-19-F-9959 | 2 | [8 empty] | 2019-07-31 |  |  | 2021-10-01 | 2042-09-30 | 23.1836 | 44787670.64 | 0 | 46983398.1 | 920559.03
2020 | MCAS Cherry Point | MCAS Cherry Point, UESC, Duke Energy, 1 | UESC | PP | See payment status (column N) | None | None | Expand FRCS capabilities and improve cybersecurity by building-out AMI and EMCS; increase electrical reliability by repairing aged switching stations; reduce energy use/costs through ltg, HVAC, water, and wastewater upgrades |  | 1 OF 20 | N/A | 11/15/2022 1/15/2023 (est) | 42768593.353 | PAID ON TIME in amount of $40,781,122.00 for construction completed to date. Large capital payment is for upfront capital cost which is being paid using hurricane recovery funds. POP extended until 15 Jan 2023 for remaining construction work. Remaining annual payments will be for service payments only in FY24 and beyond. | Post-construction, payments will only include service payments. Contract only includes Post Contraction Services for the first 10 years; years 11 through 20 are optional. | Duke Energy | N40085-20-F-9952 | 1 | [8 empty] | 2020-04-30 |  |  | 2022-11-15 | 2042-10-15 | 22.474 | 44267839 | 0 | 10754082 | 52874441.353
2019 | MCB Camp Lejeune | MCB Camp Lejeune, UESC, Duke Energy, 1 | UESC | PP | See payment status (column N) | None | None | Greatly improve reliability of water/wastewater system and controls and modernize aged ltg systems |  | 3 OF 22 |  | 12/1/2022 6/1/2023 | 3809781.36 | PREPARING FOR PAYMENT: $2,044,135.96 (TO1); FUTURE PAYMENT: $82,881.1 (TO1 – final payment). Note: Modification payments are being paid by installation as construction work is completed. | - TO1: $2,044,135.96 due 1 December 2022 - TO1M7: Obligated/Awarded 9/28 IAO $1,682,764.23 due 1 April 2023 (Extended from Dec 22) - TO1: $82,881.17 due 1 June 2023 | Duke Energy | N40085-19-F-9952 | 1 | [8 empty] | 2019-05-16 |  |  | 2022-06-02 | 2042-09-01 | 23.3123 | 54342105.6746 | 0 | 59056347.2146 | 3809781.36
2019 | MCB Camp Lejeune | MCB Camp Lejeune, UESC, Duke Energy, 3 | UESC | PP | See payment status (column N) | None | None | Expand FRCS capabilities and improve cybersecurity by installing an electrical SCADA system and EMCS and establishing a central energy operations center |  | 2 OF 21 |  | 2023-08-01 | 59782287.49 | FUTURE PAYMENT: $54,380,341.18 (TO3) Large capital payment is for upfront capital cost which is being paid using hurricane recovery funds. Note: Modification payments are being paid by installation as construction work is completed | - TO3M2: $2,107,296.59 due 1 December 2022 - TO3M4: Invoiced for $2,338,083.47 in Nov 22; payment approved; - TO3M2: $593,676.25 due 1 March 2023 - TO3M4: remaining payment is $362,890.00 due on 1 April 2023. - TO3M3: $54,380,341.18 due 1 August 2023 | Duke Energy | N40085-19-F-9960 | 3 | [8 empty] | 2019-07-31 |  |  | 2023-08-01 | 2041-06-01 | 21.8521 | 84703883.3769 | 0 | 92375334.6869 | 59782287.49
2017 | MCSF Blount Island | MCSF Blount Island, UESC, TECO, 5 | UESC | PP | See payment status (column N) | None | None | Reduced diesel use/costs for heating systems and backup generators by installing natural gas service |  | 7 OF 12 | N/A | 2022-12-01 | 437694 | PREPARING FOR PAYMENT |  | TECO | N69450-12-G-0017 | 5 | [8 empty] | 2017-09-01 |  |  | 2017-09-01 | 2029-12-01 | 12.2575 | 4684663.94 | 4684663.94 | 5595626.78 | 2565228.51
2019 | MCAS Miramar | MCAS Miramar, UESC, SDG&E, 1 | UESC | PP | See payment status (column N) | None | None | Improve Marine quality of life and reduce energy use/costs by modernizing HVAC and ltg systems in ~100 buildings, including 2,658 BEQ rooms |  | 3 OF 20 |  | 2023-02-01 | 835648.82 | FUTURE PAYMENT |  | SDG&E | N62473-18-G-5615 N62473-19-F-4704 | 1 | [8 empty] | 2019-07-21 |  |  | 2020-11-01 | 2039-11-01 | 20.2959 | 13509441 | 13509441 | 20484537 | 17348005.73
2019 | MCB Camp Pendleton | MCB Camp Pendleton, UESC, SDG&E, 22 (19.1) | UESC | PP | See payment status (column N) | None | None | Expand FRCS capabilities for metering and provide cybersecurity while also reducing energy use/costs with CCx, boiler replacements, and ltg retrofits |  | 3 OF 13 | N/A | 2023-02-01 | 1206385 | FUTURE PAYMENT |  | SDG&E | N62473-18-G-5615 DO N62473-19-F-5218 | 22 (19.1) | [8 empty] | 2019-08-30 |  |  | 2021-02-01 | 2033-02-01 | 13.4356 | 12765441 | 12765441 | 15626626.71 | 13213856.71
2015 | MCB Camp Pendleton | MCB Camp Pendleton, UESC, SDG&E, 21 | UESC | PP | See payment status (column N) | None | None | Expand FRCS capabilities by repairing DDs, building-out EMCS, and upgrading metering systems and reduce energy use/costs via RCx and ltg retrofits |  | 7 OF 7 | N/A | 2023-03-01 | 228198.32 | FUTURE PAYMENT |  | SDG&E | N62473-13-G-1403 DO #0003 | 21 | [8 empty] | 2015-09-15 |  |  | 2017-03-01 | 2023-03-01 | 7.463 | 3047193.07 | 3047193.07 | 3470628.32 | 228198.32
2020 | MCB Quantico | MCB Quantico, UESC, Dominion, 1 | UESC | D&C | See payment status (column N) | MCICOM GF-PW send MCBQ $1,526,549.00 NLT 1 February in order to make payment by 1 March, 2023. | None | Expand FRCS capabilities and improve cybersecurity by building-out AMI and EMCS; provide resiliency and demand management with 4 MW of generation; reduce energy use/costs through HVAC and ltg repairs |  | 1 OF 22 | N/A | 2023-03-01 | 13701927 | FUTURE PAYMENT | For FY23, the year 0 and year 1 (first payments) are due on 3/1/2023. Clin 0005 is the implementation period (savings) Payment Clin 0006-is payment 1 of 23 Clin 0005 still has $1,209,411.00 on it. (The payment is for $1,209,411.68) On Clin 0006- There are $322,430.00 in Funds on Clin 0006 (The payment is for $1,809,433.68). The base use some of the funds to make a modification. | Dominion | N40080-19-F-9950 | 1 | [8 empty] | 2020-09-25 |  |  | 2023-03-01 | 2044-03-01 | 23.4466 | 23944691 | 14246298.11 | 52679054 | 52300013.07
2015 | MCB Camp Lejeune (steam) | MCB Camp Lejeune (steam), UESC, Piedmont, 1 | UESC | PP | See payment status (column N) | None | None | Reduce energy use and GHGs by decentralizing coal steam plants and installing efficient building boilers |  | 7 OF 15 |  | 2023-05-15 | 2591793 | FUTURE PAYMENT |  | Piedmont | N40085-15-C-7701 | 1 | [8 empty] | 2015-03-31 |  |  | 2017-05-15 | 2031-05-15 | 16.1342 | 28709747.63 | 28709747.63 | 37898833 | 23858592.41
2021 | MCB Camp Pendleton | MCB Camp Pendleton, UESC, SDG&E, 23 | UESC | D&C | None | None | None | Improve energy efficiency, provide real time AMI tracking, Better Building Controls. Cybersecurity for FRCS MCAS, Potable Water SCADA, Electrical Distribution SCADA. Quality of Life improvements, and resiliency (Microgrid MCAS). Project will impact hundreds of buildings base-wide |  | 1 OF 7 | N/A | 2023-10-01 | 0 | FUTURE PAYMENT – Installation will pay using FY23 funds. | First payment isn't due until FY24 (10/1/2023); Base will pay using FY23 funds so the TO schedule was moved back one year to reflect proper funding allocation timeframes from USMC budget. | SDG&E | N62473-21-G-4402 DO #N6247321F5366 | 23 | [8 empty] | 2021-09-27 |  |  | 2023-10-01 | 2029-10-01 | 8.0164 | 19145595 | 7240237 | 19760732.78 | 7812700.71
2022 | MCB Camp Lejeune | MCB Camp Lejeune, UESC, Duke Energy, 5 | UESC | D&C | None | None | None | Project builds Camp Johnson Microgrid and completes roadway/area lighting upgrades and solar PV repairs. Microgrid is funded via ERCIP and other ECMs are financed via UESC. |  | 0 OF 11 | N/A | 2025-05-01 | 0 | OTHER - Per email with Lejeune on 11/7, Lejeune is waiting on a rate-lock and closing for the financed portion of the microgrid (UESC + FY18 ERCIP P-1487). Final information, including amortization tables, should be available by 12/22. |  | Duke Energy | GS00P14BSD1055 N40085-22-F-9953 | 5 | [8 empty] | 2022-09-29 |  |  | 2025-05-01 | 2035-05-02 | 12.5973 | 21725238 | 916128 | 22053188 | 1244077.9808
2023 | MCAS Beaufort | MCAS Beaufort, UESC, Dominion, 1 | UESC | IGA | J&A, Legal Sufficiency Review, and Finish IGA | Continue to engage in J&A and legal sufficiency review discussions. | None | UESC TO1, Estimated First Cost = $62M Lighting (40+ buildings; 1M SF), NG Condensing Boilers/Infrared Heaters, Renewable Energy (Solar), and Chilled Water or Ice Storage at Pilot Training Center FY19 ERCIP (P-505), Authorized Amount = $22M 20 miles of overhead to underground conversion of electrical distribution lines; transformer upgrades Provide 2.8 MW CHP; recommission propane plant; new switchgear; connect heat to thermal energy loop FY24/FY25 ERCIP (P-507), Unfunded Requested Amount = $36.6M Install 2.8 MW co-gen, 1.25 MW/2.5 MWH BESS, and 500 kW solar PV with microgrid to enhance resilience |  | TBD | N/A | 6/30/2023 |  |  |  | Dominion |  | 1
2024 | MCAS Cherry Point | MCAS Cherry Point, UESC, Duke, 2 | UESC | AQ | MCICOM Endorsed; Start PA | None | None | Close IESP gaps associated with water metering, airfield approach lighting, existing PV system functionality Enhance reliability and resiliency by installing a microgrid for critical operations, performing comprehensive repairs to the Wastewater Treatment Plant, and decentralizing steam plant Improve efficiency with targeted HVAC upgrades |  | TBD | N/A | TBD |  |  |  | Duke |  | 2
2024 | MCLB Barstow | MCLB Barstow, UESC, Southwest Gas, 1 | UESC | Advanced Planning | Opportunity Assessment provided 21 June 2022 | Wait for MCIWEST endorsement letter; route MCICOM letter for approval. | None | Provide 14+ day resilience capability and increase energy reliability by building a microgrid with solar and BESS. Repair wind turbine. Investigate a combined heat and power system during IGA. Complete facility related control system upgrades and provide cybersecurity Improve energy efficiency with HVAC and lighting upgrades, VFD control on water pumps, air compressor improvements, and irrigation controls. |  | TBD | N/A | TBD |  |  |  | Southwest Gas |  | 1
2024 | MCAS Miramar | MCAS Miramar, UESC, SDG&E, 2 | UESC | Advanced Planning | Installation developing Request Letter | Wait for MCIWEST endorsement letter; route MCICOM letter for approval. | None | Implement measures from a comprehensive Oct 2020 energy audit for base-wide HVAC, electric transformer and interior + exterior lighting upgrades, comprising 30 ECMs. Project Cost = $11M ; Savings = $968k/yr; Simple Payback = 11.4 years. Replace halogen runway centerline and edge lighting with LEDs. Replace solar PV inverters that are at end of life Assess IESP gaps and options to resolve via UESC |  | TBD | N/A | TBD |  |  |  | SDG&E |  | 2
Formulas:
Calculated Contract Term (Yrs) = DATEDIF([Award Date],[PP Last Payment Date],"d")/365
Note on C1: Kim, Irwin: The definitions below describe the various stages an ERCIP project goes through from cradle (i.e., planning) to grave (i.e., canceled, completed, or decommissioned). Proposed: Default project status that begins upon creation of a new ECIP project. These projects are proposed by the services for consideration in the ECIP Annual Budget. Budgeted: Projects are selected for inclusion in the ERCIP President’s Budget that is sent to Congress. This is only a budget assignment, actual funds have not yet been received or provided to the Components. Authorized: Status used for projects that were authorized in a National Defense Authorization Act (NDAA), whether lump sum (FY20 and earlier) or specified (FY21 and later). Appropriated: Status used for projects that were appropriated funds in an appropriations act. Enacted: Refers to an ERCIP construction project that has been authorized in an NDAA and appropriated funds in an appropriations act. P&D Distributed: Reflects the amount of funds issued via a funding document by the OSD Comptroller to a Component to provide design funds for planning and design of ERCIP construction projects. Awarded: Indicates that the funds for the project are obligated against a design or construction contract vehicle. Delayed: Refers to a completion date that has slipped to the right from the original design or construction estimated completion date (ECD), or from a previously documented, delayed completion date. Under Construction: Designates projects that are currently in the construction phase. The project is not yet on-line and is not generating any savings or producing energy Complete / Operational: Construction is complete, and the project is operational, generating energy/water savings or producing energy. Canceled: Funds allocated for this project are revoked. No portion of the project was implemented or some design or construction funds were expended, but the project did not proceed. Decommissioned: The project was operational for a period of time, generating energy/water saving or producing energy. The project reached the end of its lifecycle and was taken off line.
Note on F2: D&C = Design & Construction PP = Performance Period
Note on M2: Stefanie Judson: Typically due 3 months prior to actual due date but doesn't always work that way when payments are due at the beginning of FYs.
Note on AG12: Svetlana CIV O'Malley: POP changed due to Tme and Money MOD
Note on AK12: Svetlana CIV O'Malley: Increased contact cost from $159,992,084 to 185,268,118 due to Time and Money MOD.
Note on AF13: Svetlana CIV O'Malley: The payment on last day of Fiscal year might be a challenge
Note on L22: Stefanie Judson: SKJ With all of the mods at Lejeune, the Construction and PP periods were muddied and payments started being made in FY21 despite continued construction in FY22
Note on AJ22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Paid off entire initial construction cost.
Note on AI23: Stefanie Judson: This includes the modifications 1-4
Note on AJ23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Paid off entire initial construction cost.
Note on L24: SKJ With all of the mods at Lejeune, the Construction and PP periods were muddied and payments started being made in FY21 despite continued construction in FY22.
Note on AJ24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Paid off entire initial construction cost.
Note on AJ25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Paid off entire initial construction cost.
Note on AI33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IGA was funded via TO4 and not included in this value.

## EUL
|  |  |  | Last Updated: | 2022-12-27
Fiscal Year of Award | Installation | Project Title | Status | Next Steps | MCICOM GF-PW Action | Notes | Project Description | Mission Alignment | Service Utility | Asset | Term | Acres | IKC | Installation Request Letter Date | Region Endorsement Letter Date | MCICOM Approval Letter Date | Get Other Key EUL Dates | Get Other Key EUL Dates | Get Other Key EUL Dates | Get Other Key EUL Dates
2015 | MCB Camp Lejeune | EUL 1 | Complete | None | None | Completed FY 2016 | 25-year lease agreement for ~100 acres. 17 MW on-site solar power generation. |  | Duke Energy | Large-scale Solar | 25 | 100 | Access to power; USMC required to invest multi-millions to access power*
2015 | MCAS Yuma | EUL 1 | Complete | None | None | Completed FY 2017 | 30-year lease agreement for ~2 acres. 25 MW on-site generation microgrid. IKC- In event of grid outage, microgrid will power the installation with no impact to mission, covering 100% of current and projected base energy requirements. APS Power Generation Facility has started and maintained electrical service over 180 times since completion |  | Arizona Public Service (APS) | Power Generation with Microgrid | 30 | 2 | Access to power
2016 | MCLB Albany | EUL 1 | Complete | None | None | Completed FY 2018 | 37-year lease agreement for ~150 acres. 44 MW on-site solar power generation. IKC- New 12 MW sub-station and express feeder. USMC required to invest millions to access power* |  | Georgia Power | Large-scale Solar | 37 | 150 | Access to power
2021 | MCRD San Diego | EUL 1 | Design | Preliminary design underway; pursuing multiple power offtake opportunities. Estimated Construction Start - Spring 2023 | None | None | •35-year lease agreement for ~1.5 acres. 2.9 MW Diesel Generation. 25 MW Battery Energy . IKC- In event of grid outage, microgrid will power the installation with no impact to mission, covering 100% of current and projected base energy requirements. Based on MCAS Yuma EUL. |  | Bright Canyon Energy (BCE) | Power Generation, Storage & Microgrid | 35 | 1.5 | Access to power, secondary feed, microgrid
2024 | MCB Camp Pendleton | EUL 1 | RFP Development | RFP outline under development; 95% RFP Review Release – 28 Nov 2022; Estimated RFP Release – 7/1/2023 | Review RFP | None | TBD |  | N/A | Power Generation, Storage & Microgrid |  | TBD | Access to power. In event of grid outage, microgrid will power the installation with no impact to mission, covering 100% of current and projected base energy requirements
2024 | MCAS Yuma | EUL 2 | MCICOM Endorsement | MCICOM Real Estate approve EUL #2 | Provide Reid Merill and Ken Harris update on EUL #2. CTC understanding is that MCICOM Real Estate must sign but is waiting on MCICOM GF-PW approval to fund development efforts ($91.1K SW PW8 PM + $120K SW RE + $33.5K SW Legal + $26K SW EV = $270,600) | SKJ sent email to SH on 12/27/22 at 3 EST on topic. Pursue EUL to lease approximately 1800 acres of underutilized land for energy/utility development | TBD |  | TBD | TBD |  | 1800 | IKC - TBD
TBD | MCAS Miramar | EUL 1 | Advanced Planning | MCAS Miramar sign EUL request letter | None | May delay request until FY24. MCAS Miramar is getting guidance from Commanding Officer | TBD |  | TBD | TBD |  | TBD | IKC – TBD

## PPA
|  |  |  | Last Updated: | 2022-12-27
Fiscal Year of Award | Installation | Project Title | Status | Next Steps | MCICOM GF-PW Action | Notes | Project Description | Mission Alignment | Company | Energy Asset | Term | Acres | Installation Request Letter Date | Region Endorsement Letter Date | MCICOM Approval Letter Date | Get Other Key PPA Dates | Get Other Key PPA Dates | Get Other Key PPA Dates | Get Other Key PPA Dates
20XX | MCAS Miramar | PPA #1, LFG | Underway | [6 empty] | Landfill Gas
2023 | MCAS Miramar | PPA #2, LFG Renewal and Expansion | Advanced Planning | MCAS sign PPA request letter | None | LFG PPA renewal and capacity increase from 3.2 MW to 4.8 MW. | LFG PPA renewal and capacity increase from 3.2 MW to 4.8 MW. |  | TBD | Landfill Gas
20XX | MCRD Parris Island
20XX | MCLB Albany
20XX | MCAGCC 29 Palms
20XX | MCLB Barstow
20XX | MCB Hawaii | PPA #1, Solar PV |  |  |  |  | SolarMac. It includes Solar PV on 4 buildings, totaling just under 1.0MW.
Ideas for Tracking
| Parties | Include any changes and dates
| Term | Original term
| Extentions | Updated term
| Remaining Payments | Current amount and years remaining
| Payment Structure | Fixed payment versus delivery dependant
| M&V Date | Expected Submission. Actual Submission
| Penalties incurred | Year and amount of penalty
| Cost of Shortfall | Expense incurred of the failure to deliver
| Moneys left on the table | Expected delivery versus actual (not penalized)
| Lessons Learned | What should have been done different

## Other
[6 empty] | Last Updated: | 2022-12-27
Fiscal Year of Award | Installation | Project Type | Project # | Project Title | Status | Next Steps | MCICOM GF-PW Action | Notes / Additional Information | Project Description | Mission Alignment | Funding Amount ($)
Note on F2: Kim, Irwin: The definitions below describe the various stages an ERCIP project goes through from cradle (i.e., planning) to grave (i.e., canceled, completed, or decommissioned). Proposed: Default project status that begins upon creation of a new ECIP project. These projects are proposed by the services for consideration in the ECIP Annual Budget. Budgeted: Projects are selected for inclusion in the ERCIP President’s Budget that is sent to Congress. This is only a budget assignment, actual funds have not yet been received or provided to the Components. Authorized: Status used for projects that were authorized in a National Defense Authorization Act (NDAA), whether lump sum (FY20 and earlier) or specified (FY21 and later). Appropriated: Status used for projects that were appropriated funds in an appropriations act. Enacted: Refers to an ERCIP construction project that has been authorized in an NDAA and appropriated funds in an appropriations act. P&D Distributed: Reflects the amount of funds issued via a funding document by the OSD Comptroller to a Component to provide design funds for planning and design of ERCIP construction projects. Awarded: Indicates that the funds for the project are obligated against a design or construction contract vehicle. Delayed: Refers to a completion date that has slipped to the right from the original design or construction estimated completion date (ECD), or from a previously documented, delayed completion date. Under Construction: Designates projects that are currently in the construction phase. The project is not yet on-line and is not generating any savings or producing energy Complete / Operational: Construction is complete, and the project is operational, generating energy/water savings or producing energy. Canceled: Funds allocated for this project are revoked. No portion of the project was implemented or some design or construction funds were expended, but the project did not proceed. Decommissioned: The project was operational for a period of time, generating energy/water saving or producing energy. The project reached the end of its lifecycle and was taken off line.